## Orgranization Chart
Role | Name | Allocation | Expertise | Email | Phone | Github
Project Manager | Nhã Lý | 15 Hrs./week | Project Manager | chautrinha@gmail.com | 0814781879 | https://github.com/15110091
Data Scientist | Khoa Trần | 20 Hrs./week | Data Science | tranngockhoaspk@gmail.com | 348078809 | https://github.com/tranngockhoa
Data Scientist | Thư Trần | 15 Hrs./week | Data Science | tnmthu.maria98@gmail.com | 0902809849 | https://github.com/tnmthu
Developer (BE) | Khoa Trần | 20 Hrs./week | Data Science | tranngockhoaspk@gmail.com | 348078809 | https://github.com/tranngockhoa
Developer (FE) | Phong Hồ | 25 Hrs./week | Mobile Development | phongvanho97@gmail.com | 03426427800 | https://github.com/phong97
Developer (FE) | Hải Dương | 25 Hrs./week | Mobile Development | duongquochai123456@gmail.com | 0903585173 | https://github.com/DuongQuocHai
Tester | Nhã Lý | 10 Hrs./week | Project Manager | chautrinha@gmail.com | 0814781879 | https://github.com/15110091
Tester | Thư Trần | 15 Hrs./week | Data Science | tnmthu.maria98@gmail.com | 0902809849 | https://github.com/tnmthu
Team Resource
Github | https://github.com/201DevC
Doc | https://drive.google.com/open?id=1f2bO8X_QrTdKGfzSFkqPG1wtUJ4ArEIa
UI Design | https://www.figma.com/file/UClfOz1IfaKduN2Lhw4two/Prototyping-in-Figma?node-id=4%3A394
API Document | http://localhost:8080/swagger-ui.html

## WBS
Sendo |  |  |  | Work Breakdown Structure |  |  | Team Resource
[7 empty] | Github | https://github.com/201DevC
Project Start |  | 2019-10-13 | Project End |  | 2019-12-09 |  | Drive | https://drive.google.com/open?id=1f2bO8X_QrTdKGfzSFkqPG1wtUJ4ArEIa
Todal day |  | 48 days | [42] |  |  |  | UI Design | https://zpl.io/scene/VY1kQMJ
Level | WBS | Task Description | Assigned To | Status | Estimate (/day) | Start | End | Notes
1 | 1 | Phase 1 |  | Done | 7 | 2019-10-13 | 2019-10-18
2 | 1.1 | Wireframe and mockup | Nhã | Done | 4 | 2019-10-13 | 2019-10-17
2 | 1.2 | Setup project Structure
3 | 1.2.1 | Mobile Project | Phong, Hải | Done | 3 | 2019-10-16 | 2019-10-18 | https://github.com/201DevC/201-Mobile
3 | 1.2.2 | Backend Project | Khoa | Done | 4 | 2019-10-15 | 2019-10-18 | https://github.com/201DevC/201-Backend
3 | 1.2.3 | Data science Project | Thư, Khoa | Done |  |  |  | https://github.com/201DevC/201-DataScience
1 | 2 | Phase 2 |  |  |  | 2019-10-21 | 2019-11-02
2 | 2.1 | Login Page
3 | 2.1.1 | Login Page Design | Nhã | Done |  |  |  | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=732893540
3 | 2.1.2 | Login Page (BE) | Move to next phase
3 | 2.1.3 | Login Page (FE) | Hải | Done |  | 2019-10-26 | 2019-10-28
2 | 2.2 | Search bar and nav bar
3 | 2.2.1 | Layout App Design | Nhã | Done |  |  |  | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=588108922
3 | 2.2.2 | Layout App (FE) | Phong | In progress |  | 2019-11-02
2 | 2.3 | Collect data new user Page
3 | 2.3.1 | Collect data new user Page Design | Nhã | Done |  |  |  | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=0
3 | 2.3.2 | Collect data new user Page (BE) | Move to next phase
3 | 2.3.3 | Collect data new user Page (FE) | Hải | In progress |  | 2019-10-28 | 2019-11-02
2 | 2.4 | Home Page
3 | 2.4.1 | Home Page Design | Nhã | Done |  |  |  | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=1137849431
3 | 2.4.2 | Home Page (BE) | Move to next phase
3 | 2.4.3 | Home Page (FE) |  | Open
2 | 2.5 | Product Detail Page
3 | 2.5.1 | Product Detail Page Design | Nhã | Done | 1 | 2019-10-21 | 2019-10-26 | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=418406221
3 | 2.5.2 | Product Detail Page (BE) | Move to next phase
3 | 2.5.3 | Product Detail Page (FE) | Phong | In progress |  | 2019-11-02 | 2019-11-03
2 | 2.6 | Product by category Page
3 | 2.6.1 | Product by category Design |  | Open | 1 | 2019-10-26 | 2019-10-27
3 | 2.6.2 | Product by category (BE) | Move to next phase
3 | 2.6.3 | Product by category Page Design (FE) |  | Open
2 | 2.7 | Category Select Page
3 | 2.7.1 | Category Select Design | Nhã | Done | 1 | 2019-10-20 | 2019-10-21 | https://docs.google.com/spreadsheets/d/1tyyyHhLUS0ovyzZwJ_qMj9Y53e4NshW2a-yNxjXQ2Qs/edit#gid=646596903
3 | 2.7.2 | Category Select (BE) | Move to next phase
3 | 2.7.3 | Category Select (FE) |  | Open
2 | 2.8 | Overview Data
3 | 2.8.1 | Convert to cvs | Thư | Done | 1 | 23/10/2019 | 23/10/2019 | https://drive.google.com/drive/folders/1M-o25CxIkQdJTQ1wHW0hLUOhbKmSp6ue?usp=sharing
3 | 2.8.2 | Read paper and doc | Thư | In progress | 14 | 21/10/2019 |  | https://www.youtube.com/playlist?list=PLYi6xo6KIAoevybSRg7GAhw-36pX76kdt
3 | 2.8.3 | Analyze data | Thư | Open | 14
2 | 2.9 | Init Data for display
3 | 2.9.1 | Product Data from Sendo | Khoa | In progress | 7 | 2019-10-26 | 2019-11-01 | Có vẻ Sendo có API search trên trang web, không biết xài chùa được không. *data đang cào...
1 | 3 | Phase 3 |  |  |  | 2019-10-13 | 2019-11-16
2 | 3.1 | Login Page
3 | 3.1.1 | Login Page (BE) |  | Done |  | 2019-03-11 |  | API: http://localhost:8080/swagger-ui.html#
3 | 3.1.2 | Implement API to UI |  | Done
2 | 3.2 | Collect data new user Page
3 | 3.2.1 | Collect data new user Page (BE) |  | Done
3 | 3.2.2 | Implement API to UI |  | Done
2 | 3.3 | Search bar and nav bar
3 | 3.3.1 | Layout App (FE) | Phong | Done |  | 2019-11-02
2 | 3.4 | Home Page
3 | 3.4.1 | Home Page (FE) | Hải | Done
3 | 3.4.2 | Implement API to UI |  | Done
3 | 3.4.3 | Home Page (BE) |  | Done
3 | 3.4.4 | Product Detail Page
2 | 3.4.5 | Product Detail Page (BE) |  | Done
3 | 3.5 | Product Detail Page (FE) | Phong | Done
3 | 3.5.1 | Implement API to UI |  | Done
3 | 3.5.2 | Product by category Page/keywords Page
3 | 3.5.3 | Product by category Design |  | Done | 1
3 | 3.5.4 | (BE) |  | Done
3 | 3.5.5 | (FE) |  | Done
2 | 3.5.6 | Implement API to UI |  | Done
1 | 4 | Phase 4 |  |  |  | 2019-11-18 | 2019-11-30
2 | 4.1 | Improve UI |  | Open
3 | 4.1.1 | Create Checklist |  | Open
3 | 4.1.2 | Change design |  | Open
3 | 4.1.3 | Fix UI |  | Open
3
3
2
2